## Cover
<Tribal Land> Fixed Wireless Network – Gantt Chart
<Release Date>

## Instructions
Instructions
This template allows the user to instantiate the Gantt Chart for network design and deployment, providing a default set of ordered tasks and timelines that con be customized according to the Tribal Land plan and requirements
Template Structure
The template has a table and a chart. The chart is automatically updated based on the table data
In the table, light gray cells in columns "Start on Day" and "Duration (days)" are calculated values based on the other columns, thus, should not be edited directly
Some cells have hints and additional information. These cells have an upper right indicator:
To see the information, just hover the mouse over that cell:
Instructions
Typical use of the model includes the following steps
1. Edit the tasks to show only the tasks that apply to your project
2. Reorder tasks as required
3. Provide start and end dates for each Task
4. Verify that the chart shows the graphical timeline of your project, and apply any required adjustments to the chart format, axis and size
5. Assign a task owner
6. Register task progress periodically

## Gantt Chart
Fixed Wireless Network Project Plan
| Task Name | Start Date | End Date | Start on Day | Duration (days) | Task Owner | Percent Complete
Strategy & Business Planning
1 | Establish Service Plans & Coverage Targets | 2021-01-04 | 2021-01-15 | 0 | 12 |  | 50%
2 | Define Spectrum Strategy | 2021-01-04 | 2021-01-08 | 0 | 5 |  | 40%
3 | Collect Network Planning Data | 2021-01-18 | 2021-01-29 | 14 | 12 |  | 30%
4 | Establish Network Architecture | 2021-02-01 | 2021-02-05 | 28 | 5 |  | 20%
5 | Define Operating Model & Organization Structure | 2021-02-22 | 2021-03-05 | 49 | 12 |  | 0%
6 | Develop High Level Network & Systems Design | 2021-02-08 | 2021-02-19 | 35 | 12 |  | 0%
7 | Execute RFI for Fixed Wireless Solutions | 2021-02-15 | 2021-03-19 | 42 | 33 |  | 0%
8 | Generate Business Plan & Secure Funding | 2021-02-22 | 2021-04-02 | 49 | 40 |  | 0%
Resource Acquisition & Organization Setup
9 | Staffing | 2021-04-26 | 2021-08-16 | 112 | 113 |  | 50%
10 | Acquire resources & sign commercial agreements | 2021-04-05 | 2021-08-27 | 91 | 145 |  | 20%
11 | Headquarters Setup | 2021-04-05 | 2021-04-23 | 91 | 19 |  | 40%
12 | Staff Training & Preparation | 2021-08-16 | 2021-08-27 | 224 | 12 |  | 30%
13 | Point of Sale Setup | 2021-08-16 | 2021-08-27 | 224 | 12 |  | 20%
Network Planning & Design
14 | Execute RFP for Consulting Services | 2021-03-29 | 2021-05-07 | 84 | 40 |  | 50%
15 | Select & Onboard Consultant | 2021-05-10 | 2021-06-04 | 126 | 26 |  | 40%
16 | Develop Detailed Network Design | 2021-06-07 | 2021-06-25 | 154 | 19 |  | 40%
17 | Execute RFP for Equipment & Implementation Services | 2021-06-21 | 2021-07-16 | 168 | 26 |  | 30%
18 | Select & Onboard Vendors | 2021-07-19 | 2021-08-06 | 196 | 19 |  | 20%
19 | Site acquisition and permits | 2021-06-14 | 2021-07-09 | 161 | 26 |  | 20%
Network Deployment & Start of Operations
20 | Construction company selection and onboarding | 2021-01-04 | 2021-01-04 | 0 | 1 |  | 40%
21 | Hardware Delivery | 2021-08-09 | 2021-08-20 | 217 | 12 |  | 0%
22 | Site construction/adaptations | 2021-07-26 | 2021-08-20 | 203 | 26 |  | 0%
23 | Core Site Deployment | 2021-08-23 | 2021-08-27 | 231 | 5 |  | 0%
24 | Systems Deployment & Integration | 2021-08-23 | 2021-08-27 | 231 | 5 |  | 0%
25 | RAN Sites Deployment | 2021-08-30 | 2021-09-10 | 238 | 12 |  | 0%
26 | Customer Installation & Ongoing Operations | 2021-08-30 | 2021-09-17 | 238 | 19 |  | 0%
Formulas:
Duration (days) = DATEDIF([Start Date],[End Date],"d")+1
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task can be performed by Consultant, in which case it must be placed after selection and onboarding of them (task #15)
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task can be extended and finalized until the high-level network design is done
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task must be done to complete business plan
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Optional task for the Tribal Land. It can be performed by a consultant or by the equipment vendors as part of the RFI
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the RFI is done, the information collected informs the business plan. Thus, it should terminate before the business plan task ends
Note on C15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Staffing should start once funding has been secured and should end before or during staff training task (#12)
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Resource acquisition can start once funding has been secured and should be finalized before initiation of operations (Task #26)
Note on C18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task must be completed before initiation of operations (Task #26)
Note on C19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task should be completed before initiation of operations (Task #26)
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task should go in parallel with Site acquisition and permits (Task #19) to apply any required changes based on sites that cannot be acquired
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Start of this task may vary on whether consulting services are being utilized. If not using consulting services, it should start as soon as possible after funding is secured
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task should be done after receiving RFx responses
Note on C26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task can start after high-level design is done and funding is secured. Usually runs in parallel with detailed design
Note on C29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task starts with the purchase order after design is finalized, and must take into account vendor lead times to deliver the equipment
Note on C30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task should be completed before site deployment can begin. Ideally the end date is in sync with hardware delivery
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task can start as soon as equipment has been delivered (task #21)
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task usually runs in parallel with core site deployment
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task starts after core site and systems have been deployed
Note on C34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This task starts after the first site is in operation